## Sheet1
ID | Name | Duration | Resource Names | Notes
1 | Begin Project | 0
2 | Paint Office | 2 | Edwin Witcher
3 | Hang Pictures | 1 | Kristine Rowe | Let paint dry for one day
4 | Lay carpet | 1 | Jerold Odum, Luis Ameral | Wall-to-wall
5 | Install Furniture | 1 | Brittany Stuart, Juan Madera
6 | Project Complete | 0