## Task_Costs
ID | Active | Task_Mode | Task_Name | Fixed_Cost | Total_Cost | Baseline_Cost | Cost_Variance | Actual_Cost | Remaining_Cost
0 | Yes | Auto Scheduled | Trey_Slide_Presenter_Communicating | 0 | 44440 | 42440 | 2000 | 5360 | 39080
1 | Yes | Auto Scheduled | Phase 1 - High-Level Planning | 0 | 2620 | 1820 | 800 | 2520 | 100
2 | Yes | Auto Scheduled | Determine sales objectives | 0 | 360 | 360 | 0 | 360 | 0
3 | Yes | Auto Scheduled | Define launch goals (launch timing and publicity objectives) | 0 | 400 | 400 | 0 | 400 | 0
4 | Yes | Auto Scheduled | Establish Launch Budget | 0 | 1860 | 1060 | 800 | 1760 | 100
5 | Yes | Auto Scheduled | Identify budget requirements | 0 | 260 | 260 | 0 | 160.00000000000003 | 100
6 | Yes | Auto Scheduled | Obtain launch budget approval | 0 | 1600 | 800 | 800 | 1600 | 0
7 | Yes | Auto Scheduled | High-Level Planning Complete | 0 | 0 | 0 | 0 | 0 | 0
8 | Yes | Auto Scheduled | Phase 2 - Detailed Planning | 0 | 5520 | 4320 | 1200 | 2840 | 2680
9 | Yes | Auto Scheduled | Kickoff product launch | 0 | 320.00000000000006 | 160.00000000000003 | 160.00000000000003 | 320.00000000000006 | 0
10 | Yes | Auto Scheduled | Marketing | 0 | 2800 | 1760 | 1040 | 2520 | 280
11 | Yes | Auto Scheduled | Define press release requirements | 0 | 200 | 200 | 0 | 200 | 0
12 | Yes | Auto Scheduled | Define sales presentations | 0 | 1360 | 720 | 640 | 1080 | 280
13 | Yes | Auto Scheduled | Define product specification literature | 0 | 640.00000000000011 | 640.00000000000011 | 0 | 640.00000000000011 | 0
14 | Yes | Auto Scheduled | Define internal communication needs | 0 | 600.00000000000011 | 200 | 400.00000000000006 | 600.00000000000011 | 0
15 | Yes | Auto Scheduled | Engineering | 0 | 480 | 480 | 0 | 0 | 480
16 | Yes | Auto Scheduled | Align product release timing with marketing plan | 0 | 480 | 480 | 0 | 0 | 480
17 | Yes | Auto Scheduled | Manufacturing | 0 | 1120 | 1120 | 0 | 0 | 1120
18 | Yes | Auto Scheduled | Prepare for volume manufacturing according to sales goals | 0 | 1120 | 1120 | 0 | 0 | 1120
19 | Yes | Auto Scheduled | Sales | 0 | 320.00000000000006 | 320.00000000000006 | 0 | 0 | 320.00000000000006
20 | Yes | Auto Scheduled | Plan sales force staffing and training to support sales goals | 0 | 320.00000000000006 | 320.00000000000006 | 0 | 0 | 320.00000000000006
21 | Yes | Auto Scheduled | Product Support | 0 | 480 | 480 | 0 | 0 | 480
22 | Yes | Auto Scheduled | Plan team staffing to support sales goals | 0 | 480 | 480 | 0 | 0 | 480
23 | Yes | Auto Scheduled | Detailed Planning Complete | 0 | 0 | 0 | 0 | 0 | 0
24 | Yes | Auto Scheduled | Phase 3 - Execution | 0 | 19900 | 19900 | 0 | 0 | 19900
25 | Yes | Auto Scheduled | Marketing | 0 | 6380 | 6380 | 0 | 0 | 6380
26 | Yes | Auto Scheduled | Evaluate market and refine messaging | 0 | 200 | 200 | 0 | 0 | 200
27 | Yes | Auto Scheduled | Create press releases | 0 | 340.00000000000006 | 340.00000000000006 | 0 | 0 | 340.00000000000006
28 | Yes | Auto Scheduled | Create product specification literature | 0 | 1600 | 1600 | 0 | 0 | 1600
29 | Yes | Auto Scheduled | Create sales presentations | 0 | 1800 | 1800 | 0 | 0 | 1800
30 | Yes | Auto Scheduled | Create sales, field, and product support training | 0 | 1800 | 1800 | 0 | 0 | 1800
31 | Yes | Auto Scheduled | Update product forecasts based on market feedback and analysis | 0 | 320.00000000000006 | 320.00000000000006 | 0 | 0 | 320.00000000000006
32 | Yes | Auto Scheduled | Update launch plan based on forecast | 0 | 320.00000000000006 | 320.00000000000006 | 0 | 0 | 320.00000000000006
33 | Yes | Auto Scheduled | Engineering | 0 | 4800.0000000000009 | 4800.0000000000009 | 0 | 0 | 4800.0000000000009
34 | Yes | Auto Scheduled | Complete and test product | 0 | 4800.0000000000009 | 4800.0000000000009 | 0 | 0 | 4800.0000000000009
35 | Yes | Auto Scheduled | Manufacturing | 0 | 8000 | 8000 | 0 | 0 | 8000
36 | Yes | Auto Scheduled | Create prototype products | 0 | 6400 | 6400 | 0 | 0 | 6400
37 | Yes | Auto Scheduled | Prepare pipeline | 0 | 1600 | 1600 | 0 | 0 | 1600
38 | Yes | Auto Scheduled | Sales | 0 | 400 | 400 | 0 | 0 | 400
39 | Yes | Auto Scheduled | Establish sales channels | 0 | 400 | 400 | 0 | 0 | 400
40 | Yes | Auto Scheduled | Product Support | 0 | 320.00000000000006 | 320.00000000000006 | 0 | 0 | 320.00000000000006
41 | Yes | Auto Scheduled | Establish product support mechanisms | 0 | 320.00000000000006 | 320.00000000000006 | 0 | 0 | 320.00000000000006
42 | Yes | Auto Scheduled | Execution Phase Complete | 0 | 0 | 0 | 0 | 0 | 0
43 | Yes | Auto Scheduled | Phase 4 - Release To Manufacture | 0 | 16400 | 16400 | 0 | 0 | 16400
44 | Yes | Auto Scheduled | Manufacturing | 0 | 10600 | 10600 | 0 | 0 | 10600
45 | Yes | Auto Scheduled | Certify product | 0 | 1000 | 1000 | 0 | 0 | 1000
46 | Yes | Auto Scheduled | Manufacture the volume of product planned to meet sales objectives. | 0 | 9600.0000000000018 | 9600.0000000000018 | 0 | 0 | 9600.0000000000018
47 | Yes | Auto Scheduled | Sales | 0 | 3600 | 3600 | 0 | 0 | 3600
48 | Yes | Auto Scheduled | Hire and train sales staff | 0 | 3600 | 3600 | 0 | 0 | 3600
49 | Yes | Auto Scheduled | Product Support | 0 | 1600 | 1600 | 0 | 0 | 1600
50 | Yes | Auto Scheduled | Hire and train product support personnel | 0 | 1600 | 1600 | 0 | 0 | 1600
51 | Yes | Auto Scheduled | Final Quality Review | 0 | 600.00000000000011 | 600.00000000000011 | 0 | 0 | 600.00000000000011
52 | Yes | Auto Scheduled | Conduct final quality review | 0 | 600.00000000000011 | 600.00000000000011 | 0 | 0 | 600.00000000000011
53 | Yes | Auto Scheduled | Product Release Information Complete | 0 | 0 | 0 | 0 | 0 | 0
54 | Yes | Auto Scheduled | Needed materials are on order or in stock. | 0 | 0 | 0 | 0 | 0 | 0
55 | Yes | Auto Scheduled | Literature Complete | 0 | 0 | 0 | 0 | 0 | 0
56 | Yes | Auto Scheduled | Training Complete | 0 | 0 | 0 | 0 | 0 | 0
57 | Yes | Auto Scheduled | Launch Product | 0 | 0 | 0 | 0 | 0 | 0